## Schedule of values
Schedule of values and progress billing template
Bolster · bolsterbuilt.com/payments · Replace the example lines with your job. Yellow cells are inputs; the rest calculate.
Project | Kitchen and main floor renovation (example)
Pay application # | 2
Retainage % | 10%
Previous payments | 18000
# | Line item | Scheduled value | % complete to date | Work completed to date | Balance to finish
1 | General conditions and permits | 8000 | 40%
2 | Demolition and disposal | 6500 | 100%
3 | Framing and structural | 12000 | 100%
4 | Plumbing | 11500 | 50%
5 | Electrical | 10500 | 50%
6 | HVAC | 5000 | 40%
7 | Insulation and drywall | 9000 | 25%
8 | Cabinets and countertops | 28000 | 0%
9 | Flooring | 9500 | 0%
10 | Tile and backsplash | 6000 | 0%
11 | Painting | 5000 | 0%
12 | Trim, fixtures and finish carpentry | 7000 | 0%
13 | Final cleanup and punch list | 2000 | 0%
14
15
16
17
18
19
20
21
22
23
24
25
Contract sum
Total completed to date
Percent complete
Less retainage
Earned less retainage
Less previous payments
AMOUNT DUE THIS PERIOD
Balance to finish (incl. retainage)
Not legal or accounting advice. Retainage and lien waiver rules vary by state.